PROJECT SCHEDULE

Below is an outline of anticipated project schedule.  These dates are based on Covered California’s estimates of high-level project steps and timeframes understood to be required for successful project implementation and service over the contract period.

Contractor is to provide a project schedule with their bid submission.  Schedule is to include overview description of Contractor’s proposal for transitioning to Contractor’s solution.

Covered California recognizes the Contractor project schedule may not match the project schedule provided below.  This stated, please note the following components that are key project schedule considerations:

| “Pre-Implementation” period | This is a period where Contractor and Covered California work to establish business rule, policy, and process details. |
| --- | --- |
| Avoiding disruption during heavy volume | Like the rest of the California small business market, CCSB sees a significant amount of group renewals in the months of November, December, and January. As such, to help ensure high service levels, planning currently is designed to not have transition to the selected solution during these months. |
| Go-Live Ramp-up of Contractor Solution | A period where the Contractor’s Solution is run in parallel to the currently in place operation is anticipated. The intent of this is to allow for Solution validation and adjustments as indicated prior to full go-live. |
| Full Go-Live Activation of Contractor Solution | 4/1/2021 (Mandatory date to be met). |